## Prozess FMEA
Prozess FMEA
FMEA-Typ: |  | Process
System/Subsystem/Element: |  | Cordless Drill Assembly – Final Assembly & Testing
Verantwortlicher FMEA-Leiter: |  | Max Mustermann
Datum/Version: |  | 04.05.2026
Änderungsstand: |  | V1.0 Example
Verknüpfung zur nächsten Ebene: |  | Production Control Plan / Work Plan / Control Plan
Step Number | Process Map – Activity | Key Process Inputs | Potential Failure | Potential Failure Effect | Severity (S) | Potential Causes | Occurrence (O) | Current Controls | Detection (D) | Risk Priority Number (RPN) | Action Priority (AP) | Recommended Actions | Responsibility | Planned End Date | Actions Implemented | Actual End Date | Severity (S) | Occurrence (O) | Detection (D) | Risk Priority Number (RPN) | Action Priority (AP)
1 | Receiving and storage of battery cells | Approved cell batch, inspection certificate, storage conditions 20–25 °C | Incorrect or damaged cell batch is released for assembly | Reduced battery performance; possible overheating during operation; complaints and safety risk | 10 | Supplier mix-up; missing FIFO labeling; incomplete incoming goods inspection | 3 | Supplier approval; incoming goods inspection by sampling; barcode scan of batch | 5 | 150 | M | 100% scan of cell batch with blocking logic in ERP; clear FIFO racks; expand inspection plan to include visual check for transport damage | Incoming Goods Quality | 2026-06-15 | Yes | 2026-06-12 | 10 | 2 | 3 | 60 | L
2 | Inserting and fastening motor/gearbox unit | Torque specification 1.8 Nm; approved screws; calibrated screwdriver | Screw joint tightened with incorrect torque | Loosening during operation; noise development; failure of power transmission | 8 | Incorrect screw program; bit wear; calibration interval exceeded | 5 | Torque monitoring in screwdriver; daily functional check; operator instruction | 4 | 160 | M | Lock screw program by barcode; automatic calibration reminder; introduce bit replacement by counter reading | Production / Maintenance | 2026-06-30 | Partial | 2026-06-28 | 8 | 3 | 3 | 72 | L
3 | Soldering or contacting motor leads | Soldering parameters, cable harness, connectors, ESD protection | Cold solder joint or contact not fully latched | Intermittent failure; motor does not start reliably; rework or field failure | 7 | Soldering temperature too low; contaminated contact surface; missing pull test | 4 | Visual inspection; soldering station process release; ESD workstation | 6 | 168 | M | Add pull test as a 100% inspection; monitor and log soldering parameters; use Poka-Yoke for connector latching | Manufacturing Engineering | 2026-07-10 | No |  | 9 | 2 | 3 | 54 | L
4 | Final test of function and safety lock | Test adapter, test software, limit values for speed/current, test instruction | Faulty safety lock is not detected in the final test | Unintended switch-on at the customer; risk of injury; recall risk | 10 | Test step not included in sequence; test adapter does not clearly detect switch position; limit value maintained incorrectly | 3 | End-of-line functional test; test software versioning; release by QA | 7 | 210 | H | Block lock test step as a mandatory test in EOL software; version-controlled limit values; daily master-part test | Quality / Test Engineering | 2026-07-31 | No |  | 10 | 2 | 3 | 60 | L